## Project Planner
Remote Automation
using optical fibre communication
by Anthony Baudinette & Jarred Paola
ACTIVITY |  | Start | Duration | PERCENT COMPLETE | SEM 1 | [11 empty] | Mid-Year | SEM 2 | [11 empty] | End-Year
| Description |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Literature review | Research and explore previous works regarding optical fibre and remote communications. | 1 | 2 | 100%
Risk and Requirements docs | Documents to outline predicted and forseeable risks and project milestones. | 2 | 2 | 100%
Communicate with black box | Ability to establish link and send/receive information with a device. | 3 | 1 | 100%
| Talk to local port on computer. | 2 | 1 | 0%
| Receive information from black box at local port. | 3 | 1 | 0%
SSH tunneling method | Method of establishing a tunnel between one computer and another. | 4 | 3 | 100%
| Research possible methods of tunnel connection. | 4 | 2 | 0%
| Decide and implement tunnel connection. | 5 | 2 | 0%
Use device through SSH tunnel | Setting specified instructions to a device to obtain desired data back from device through communication tunnel. | 7 | 4 | 100%
| Send/receive information from device on other side of tunnel. | 7 | 2 | 0%
| Run commands and standard use of device through tunnel. | 9 | 2 | 0%
Automated scripts via SSH tunnel | Running scripts through tunnel on another computer for target device. | 11 | 7 | 100%
| Set up script to run multiple times. | 11 | 2 | 0%
| Set up script to save all results from multiple runs. | 13 | 2
| Implement automated scripts via ssh tunnel | 15 | 3 | 0%
Handoff material | Develop user manual to handoff for potential users to implement and use system for remote automation | 20 | 3 | 100%
| Pull github code on anonymous computer to replicate work | 20 | 1 | 0%
| User manual for how to use and implement such technique on personal system | 21 | 2 | 0%
FYP material | Thesis paper, poster, video, and presentation to academic team, culminating in Spark Night | 16 | 9 | 100%